## Sheet1
Ticket No | Subject | Description | Status
AMSC-83 | Create DevOps coverage plan for next 2 months | Disaster Recovery plan | Pending
AMSC-35 | Load Testing using serverless-artillery | Need to discuss with Praveen | Pending
AMSC-120 | 12 week DevOps Backlog | • Resize the volume. - Completed • Remove the disconnected Wazuh agents. - Completed • Increase the ram on playsearch servers. - Pending • Upgrade the Wazuh agents. - Completed | 3 Completed 1 Pending
AMSC-233 | DevSecOps dashboard | Creating Dashboard on Wazuh | Completed
AMSC-123 | The newly created environment not supporting purge functionality (Message Retention) | Need to discuss with Praveen | Pending
AMSC-250 | Email Alerts Monitoring - Report | John is updating daily | Completed
AMSC-431 | User Setup in play-dev1 and play-qa2 | • User Setup completed for Winfield - Completed • Need to complete for John and Saurabh | Inprogress
AMSC-516 | Identify the possibilities of AWS cost saving for AMSConnect | Completed | Completed
AMSC-418 | All Mid Coast users are receiving a SAML error and unable to log in | It is already completed by Paramanand dubey | Completed
AMSC-514 | Nagios Problem Service Alert from Playdb and Livedb | We have extended the root filesystem on both servers | Completed
AMSC-263 | Environment Name Modification |  | Pending
AMSC-480 | Required - a detailed account of what/when/where/etc of various backups for AMSConnect |  | Completed
AMSC-502 | Upgrade Wazuh on Live Environment |  | Completed
AMSC-521 | Removing Disconnected Wazuh Agents |  | Completed
AMSC-474 | iOS devices cannot open the ADFS website correctly from within the AMS Connect application |  | Pending
AMSC-554 | Adding Live and Play Search servers for memory check on Nagios | Confiuged play-qa2 search1 server. Will be adding remaining servers | Inprogress
AMSC-591 | Remove PD Credentials |  | Inprogress
AMSC-592 | Find the S3 Bucket Store Cost |  | Inprogress

## Sheet2
Ebs volume cost |  | Ec2 Instance Cost
gp3 volume cost per Month | 505.6 | Total INTEL instances cost per month | 1827.93
gp2 volume cost per Month | 627.84 | Total AMD instances cost per month | 1666.49
Cost saved per month | 122.24 | Total cost saved per Month | 161.44

## Sheet3
Sr No | Task | Project | status
1 | Took DB Backup on live and play | AMS | Done
2 | Checked all the monitoring tools | AMS | Done
3 | Provided KT to Rahul | AMS | Done
4 | Preparing document for instance type change | AMS | Inprogress
5 | Send email to the client for aws cost savings. | AMS | Done